## Document_Coverage
Block | Subsystem | Required_Knowledge | Available_Documents | Missing_Documents | Priority | Impact_If_Missing | Status | Gate | source_ids
LAB | TesPro TG-524 (OpenWrt lab DUT) | Port map, RS485, DI/DO limits, OpenWrt SDK, Secure Boot / TPM | TG-500 datasheet; spec response form; lab platform freeze doc | OpenWrt SDK from TesPro; confirmed SKU TG-424 vs TG-524 | P0 | Cannot cross-compile or run on-target tests until SDK + hardware | PARTIAL | Lab bring-up | ccli-tg500-lab-platform; ccli-tespro-tg500-ds; ccli-tespro-tg424-response
MOCK | Raspberry Pi (pre-hardware mock) | Same test vectors as TG-524; pymodbus + libiec61850 native build | Validation strategy; mocking bench BOM; protocol library refs | apps/ccli scaffold; Pi validation runbook | P0 | Delayed L1/L2 protocol work before TG-524 arrives | PARTIAL | Wave A | ccli-validation-strategy; ccli-mocking-bench-bom; ccli-github-protocol-libs
C1 | Ethernet — Eth_A / Eth_B / Plant×2 | 4-domain isolation; switch vs dual-PHY; GOOSE L2; magjacks; EMC Ethernet | CEI Allegato O/T; Network_Architecture.drawio; Interface_Matrix; Prototype BOM category; Validation strategy | C1 topology ADR (locked); Switch/PHY DS (MPN); Magjack DS; Pin budget for Ethernet pins | P0 | Wrong segmentation → grid rejection; GOOSE/MMS failure; carrier respin | MISSING | D3/D12 + ADR-005 | cei-0-16-allegato-o; cei-0-16-allegato-t; ccli-prototype-bom
C2 | 2× Isolated RS485 Modbus RTU | Opto-isolated transceiver; RJ45 8/8 plant serial; EMC; termination | Vendor selection C2; Interface_Matrix; SK0146 RS485 sheet (on disk, NOT in RAG); ATEX reuse craft | Isolated RS485 transceiver DS (MPN); Connector pinout freeze; SK0146 RAG ingest | P1 | Schematic hold on C2; wrong EMC scope if kit DB9 used as product proof | MISSING | D13 | ccli-vendor-selection; sk0146-blk_ref_a_rs485 (NOT_IN_RAG)
C3 | Protocols — IEC61850 / IEC104 / Modbus | MMS, GOOSE, 60870-5-104, Modbus TCP/RTU; commercial 61850 license | CEI O/T; Validation strategy; GitHub libiec61850/lib60870 refs; Mocking bench SW list; Regs classification | GOOSE lab runbook; IEC104 stack choice + test vectors; MZ commercial license quote; Analyzer Modbus map | P0 | Cannot prove DSO/operator path; legal risk shipping GPLv3; plant poll blocked | PARTIAL | D-LIC / D8 | cei-0-16-allegato-o; ccli-validation-strategy; ccli-project-roadmap
C4 | DI 10–120 Vdc ×5 + DO dry contact ×3 | Opto DI conditioner; relay class; surge; PF2 failsafe; Wave B fixture | Vendor selection C4; Validation + Mocking Bench BOM Wave B; SK0146 DIN/DOUT (craft only) | Opto DI DS (MPN); Relay DS (MPN); Contact VA rating; HW WDT→DO failsafe note | P1 | False curtailment / unsafe DO; cannot freeze schematic C4 | MISSING | D11 | ccli-vendor-selection; ccli-mocking-bench-bom; ccli-validation-strategy
C5 | GNSS time sync (NMEA + PPS) | Module UART/I2C; PPS GPIO; antenna; industrial temp; optional PTP | Vendor selection C5; Prototype BOM category; Power_Tree stub; Validation L3 deferred note | GNSS module DS (MPN); Antenna DS; PPS pin in pin budget; PTP requirement decision | P1 | Event timestamp mismatch; L3 time tests blocked | MISSING | D9 | ccli-prototype-bom; ccli-vendor-selection
C6 | Secure Boot + Secure Element | HAB fuse policy; signed image CI; SE/TPM key storage; 62443 zones | TG-524 Secure Boot / TPM brochure; Architecture framework; Regs class; protocol libs | Product key hierarchy doc; SE/TPM DS (MPN or SoM SKU proof); IEC 62443 SL/zones diagram; 62351 test plan | P0 | Cyber assessment fail; keys in filesystem (R-SEC-001) | PARTIAL | D15 / D-CERT | ccli-tg500-lab-platform; ccli-github-protocol-libs; ccli-cci-module-regs-class
C7 | LTE backup (optional rev A) | Cat.1 module; antenna; SIM; firewall vs Eth_A | Prototype BOM partial; Quectel-class refs in Telematry; Vendor selection optional | CCI-locked LTE module DS; RF/antenna layout guide for carrier | P3 | Rev A slip only — must not block Architecture Freeze | PARTIAL | D10 | ccli-prototype-bom
C8 | Local console / commissioning USB | USB out of cert path; RBAC; physical access | Dev Board USB; Architecture framework; Interface_Matrix | Commissioning security procedure (62443) | P2 | Attack surface if USB unconstrained | PARTIAL | — | ccli-toradex-verdin-devboard; ccli-architecture-framework
C9 | Mechanical / DIN-rail enclosure | Thermal envelope; connector placement; IP rating if required | Prototype BOM category; Architecture mech note | Enclosure drawing; Thermal budget; Connector family freeze | P2 | PCB/enclosure mismatch; thermal failure in cabinet | MISSING | D18 | ccli-prototype-bom
C10 | Power — 12–24 Vdc isolated input | Isolated DC-DC; sequencing; eFuse; brownout; load budget; DI field supply independence | Power_Tree.drawio (conceptual); Prototype BOM C10 category; Kit 7–24 V note | PSU module DS (MPN); Current/load budget; Hold-up / brownout analysis | P1 | Field brownout; relay dropouts; SoM reset under load | MISSING | D14 | ccli-prototype-bom
SYS | System architecture & CEI PF2 | Annex O/T PF2; Eth domains; curtailment safe-state; verification L1–L4 | Architecture Framework; DRB CCLI-DRB-001; draw.io set; Interface/BOM/Risk/Verification matrices; architecture.db; CEI O/T | Pin budget; Carrier freeze doc; C1 ADR locked | P0 | Architecture Freeze remains NO-GO | PARTIAL | D0/D3/D4 | ccli-architecture-framework; ccli-design-review-board-pf2; cei-0-16-allegato-o
VAL | Validation / mocking bench | Wave A–D fixtures; GOOSE/MMS/104/Modbus tests; evidence paths | Validation strategy (INGESTED); Mocking Bench BOM (INGESTED); Verification_Matrix | GOOSE test procedure; IEC104 client choice; Real analyzer register map; Evidence folder convention | P1 | False confidence from kit-only tests; delayed L2/L3 | PARTIAL | — | ccli-validation-strategy; ccli-mocking-bench-bom
SEC | Cybersecurity / IEC 62443 / CRA | Zones/conduits; SL-T; CRA; secure boot ceremony | Regs classification; EU CRA PDF on disk; RED directive PDF; GitHub security layers | 62443 zones diagram; SL target; Licensed 62443/62351 extracts; Key ceremony SOP | P0 | Certification delay; weak product security story | PARTIAL | D-CERT | ccli-cci-module-regs-class; eu-2024-2847-cra
FIELD | Custom field CCI (deferred) | Future product carrier — not Phase 1 lab | Historical study in _archive/som-study/ | Field product architecture TBD | — | N/A for lab | DEFERRED | Post-lab | —

## Missing_Documents
Doc_ID | Document | Subsystem | Target_Path | source_id | Priority | Impact | Action | Blocks_Gate
MD-001 | TesPro OpenWrt SDK | LAB | vendor package | ccli-soc-freeze | P0 | Cannot cross-compile for TG-524 | Request with TG-524 PO | Lab bring-up
MD-002 | TG-424 vs TG-524 SKU confirmation | LAB | vendor email / PO | ccli-tg500-lab-platform | P0 | Wrong device ordered | Confirm with TesPro FAE | PO
MD-003 | Lab port map (Eth_A/B/plant labels) | LAB | 08-engineering/CCI_TG500_Lab_Platform.md | ccli-tg500-lab-platform | P0 | Blocks L2 HIL wiring | Label ports on receipt | L2
MD-004 | CCI Carrier Block Diagram (frozen) | Carrier | 08-engineering/CCI_Carrier_Block_Diagram.md | ccli-carrier-block | P0 | No Altium-ready freeze; C1/C2/C4/C5 open | Export/freeze from Hardware_Architecture.drawio | D4
MD-005 | C1 Ethernet topology ADR (locked) | C1 Ethernet | Architecture ADR-005 → Accepted | ccli-architecture-framework | P0 | Wrong network segmentation; GOOSE failure | DRB decide switch vs dual PHY; update ADR-005 | Arch Freeze
MD-014 | Product key hierarchy / HAB ceremony SOP | C6 Security | 08-engineering/CCI_Secure_Boot_Key_Hierarchy.md | ccli-secure-boot-keys | P0 | Secure Boot theater without process | Author before Hardware Freeze | HW Freeze
MD-015 | IEC 62443 zones & conduits + SL target | Security | 08-engineering/CCI_62443_Zones.md | ccli-62443-zones | P0 | Security compliance gap | Architecture workshop; map Eth_A/B/plant/USB/LTE | D-CERT
MD-018 | GOOSE lab test procedure | C3 / Validation | 08-engineering/CCI_GOOSE_Test_Procedure.md | ccli-goose-test | P0 | Incorrect curtailment/event behavior | Author from validation strategy + Wave A | Arch Freeze
MD-022 | SK0146 schematic RAG ingest | Reuse / Bench | Telematry rag-structured/sk0146/ | sk0146-schematic-index | P0 | Knowledge leak during FCT/debug; lost reuse | Run ingest-sk0146-schematics.ps1 | D-SK0146
MD-006 | Ethernet switch / PHY datasheet | C1 Ethernet | reference/<MPN>-switch-phy.pdf | ccli-bom-switch-phy | P1 | Cannot complete C1 schematic | Select MPN after ADR-005 + pin budget | D12
MD-007 | RJ45 magjack datasheet ×4 | C1 Ethernet | reference/<MPN>-magjack.pdf | ccli-bom-magjack | P1 | EMC/layout risk | Select with PHY/switch | D12
MD-008 | Opto-isolated RS485 transceiver DS ×2 | C2 RS485 | reference/<MPN>-rs485.pdf | ccli-bom-rs485 | P1 | C2 schematic hold | Select industrial isolated MPN | D13
MD-009 | DI opto conditioner DS (10–120 V) | C4 Digital I/O | reference/<MPN>-di.pdf | ccli-bom-di | P1 | False PF2 / channel damage | Select after Wave B 24V learnings | D11
MD-010 | DO relay datasheet (dry contact) | C4 Digital I/O | reference/<MPN>-relay.pdf | ccli-bom-do | P1 | Curtailment contact unreliable | Spec VA + inductive load class | D11
MD-011 | GNSS module + antenna DS | C5 GNSS | reference/<MPN>-gnss.pdf | ccli-bom-gnss | P1 | No PPS/timestamp path | Select u-blox-class with PPS | D9
MD-012 | 12–24 V isolated PSU / DC-DC DS | C10 Power | reference/<MPN>-psu.pdf | ccli-bom-psu | P1 | Brownout / field failure | Size for SoM+PHY+relays+inrush | D14
MD-013 | Secure element / TPM datasheet | C6 Security | reference/<MPN>-se.pdf or SoM SKU letter | ccli-bom-se | P1 | Keys in filesystem; 62443 fail | Pick ATECC/STSAFE/SE050 or prove on-SoM TPM | D15
MD-016 | MZ Automation libiec61850 commercial quote | C3 Protocols | procurement quote | ccli-project-roadmap | P1 | Legal risk shipping GPLv3 | Request quote before product | D-LIC
MD-017 | Energy analyzer Modbus register map | C2/C3 | 07-protocols/… | ccli-modbus-analyzer-map | P1 | L3 plant serial software blocked | Pick analyzer model; extract map | D8
MD-019 | IEC 60870-5-104 simulator choice + vectors | C3 Protocols | 08-engineering/CCI_IEC104_Lab.md | ccli-iec104-lab | P1 | Operator Eth_B integration delay | Pick lib60870 or licensed client; write vectors | FW Dev
MD-020 | Power load + thermal budget | C10 / C9 | 08-engineering/CCI_Power_Thermal_Budget.md | ccli-power-thermal | P2 | Cabinet overheating; PSU undersize | Expand Power_Tree with currents | PCB
MD-021 | DIN-rail enclosure drawing | C9 Mechanical | mechanical drawing | ccli-enclosure | P2 | Form-factor / connector clash | Select enclosure after thermal envelope | D18
MD-023 | EMC connector family (RJ45 8/8) part PNs | C1/C2 EMC | reference + D19 freeze | ccli-emc-connectors | P2 | Certification failures | Freeze pinout + magnetics family | D19
MD-024 | Altium ActiveBOM export | Carrier | after schematic | — | P2 | Fab BOM incomplete | Export after D3/D4 + MPN lock | D7
MD-025 | Design Review Board ingest to RAG | SYS | knowledge-base/08-engineering/CCI_Design_Review_Board_PF2.md | ccli-design-review-board-pf2 | P2 | DRB not queryable in BizChat/RAG | ingest-ccli.ps1 for DRB MD | —

## Knowledge_Risk_Matrix
KR_ID | Knowledge_Area | Current | Required | Risk | Impact | Priority | Mitigation | Target_Gate | rag_source_id
KR-001 | IEC 61850 MMS | Low | High | High | Communication failure with DSO | Critical | Study IEC61850 docs + lab validation | Architecture Freeze | cei-0-16-allegato-o
KR-002 | IEC 61850 GOOSE | None | High | High | Incorrect event/curtailment behavior | Critical | Build GOOSE test environment | Architecture Freeze | ccli-validation-strategy
KR-003 | Lab platform integration | Medium | High | Medium | Delayed on-target tests | Critical | Order TG-524; request OpenWrt SDK; label port map | Lab bring-up | ccli-tg500-lab-platform
KR-004 | Linux Boot Chain | Low | High | Medium | System startup failures | High | Learn U-Boot and Linux boot flow on TG-524 OpenWrt | Hardware Freeze | ccli-tg500-lab-platform
KR-005 | Secure Boot | None | High | High | Cybersecurity vulnerability | Critical | Study TG-524 Secure Boot / TPM path with TesPro SDK | Hardware Freeze | ccli-tg500-lab-platform
KR-006 | Secure Element | None | Medium | Medium | Weak key management | High | Prototype SE050 / ATECC608B / STSAFE | Hardware Freeze | ccli-prototype-bom
KR-007 | Ethernet Switch Architecture | Low | High | High | Wrong network segmentation | Critical | Study managed switch design; write C1 ADR | Architecture Freeze | ccli-prototype-bom
KR-008 | IEEE1588/PTP | None | Medium | Medium | Time synchronization errors | High | Confirm CEI need; GNSS/PTP test bench if required | System Integration | ccli-vendor-selection
KR-009 | GNSS Timing | Low | Medium | Medium | Event timestamp mismatch | Medium | Prototype GNSS + PPS integration | System Integration | ccli-prototype-bom
KR-010 | IEC 60870-5-104 | Low | Medium | Medium | Utility integration delay | High | Implement IEC104 simulator | Firmware Development | cei-0-16-allegato-t
KR-011 | Linux Networking | Medium | High | Medium | Routing/firewall issues | High | Lab validation VLAN/firewall on kit | Architecture Freeze | ccli-validation-strategy
KR-012 | IEC 62443 | None | Medium | High | Security compliance gap | Critical | Security architecture review; zones/conduits | Architecture Freeze | ccli-cci-module-regs-class
KR-013 | Thermal Design | Medium | High | Medium | Overheating in cabinet | Medium | Thermal simulations + power budget | PCB Layout | ccli-prototype-bom
KR-014 | EMC for Ethernet | Medium | High | Medium | Certification failures | High | EMC design review on product carrier | PCB Layout | ccli-vendor-selection

## Learning_Roadmap
Priority | Topic | Target_Before | KR_Primary | KR_Secondary | Phase_Order
Critical | IEC 61850 MMS + GOOSE | Architecture Freeze | KR-001 | KR-002 | 1
Critical | Ethernet C1 topology (switch vs PHY) | Architecture Freeze | KR-007 |  | 2
Critical | IEC 62443 zones / SL target | Architecture Freeze | KR-012 |  | 3
Critical | Secure Boot + key ceremony | Hardware Freeze | KR-005 | KR-004 | 4
Critical | Carrier design + pin budget D3/D4 | Schematic Capture | KR-003 |  | 5
High | Secure Element prototype | Hardware Freeze | KR-006 |  | 6
High | IEC 60870-5-104 simulator | Firmware Development | KR-010 |  | 7
High | Linux networking / firewall lab | Architecture Freeze | KR-011 |  | 8
High | PTP (only if required) | System Integration | KR-008 |  | 9
Medium | GNSS / PPS | System Integration | KR-009 |  | 10
Medium | Thermal design | PCB Layout | KR-013 |  | 11
Medium | EMC Ethernet optimization | PCB Layout | KR-014 |  | 12
Low | LTE integration | Rev A |  | Reuse ATEX | 13
Low | RS485 / Modbus craft | Ongoing |  | Reuse SK0146/ATEX | 14

## Heat_Map
Band | Topic | Note
Critical | IEC61850 (MMS+GOOSE) | Delays whole project
Critical | Carrier Board Design | Delays whole project
Critical | Secure Boot | Delays whole project
Critical | Ethernet Architecture | Delays whole project
Critical | IEC62443 | Delays whole project
High | IEC104 | Needed before architecture freeze
High | Linux Networking | Needed before architecture freeze
High | Secure Element | Needed before architecture freeze
High | PTP (if required) | Needed before architecture freeze
Medium | GNSS | Needed before PCB release
Medium | Thermal Design | Needed before PCB release
Medium | EMC Optimization | Needed before PCB release
Low | LTE Integration | Covered by previous experience
Low | RS485 | Covered by previous experience
Low | Modbus | Covered by previous experience
Low | Power Supply Basics | Covered by previous experience

## Reuse_Matrix
Area | Reuse_from_ATEX | Caution
RS485 | High | Product needs opto RJ45 — not kit DB9
LTE | High | Rev A optional
Digital Inputs | High | Craft only — CCI 10-120V ≠ SK0146 3.3V
Relay Outputs | High | Craft only — dry contact rating TBD
Power Protection | High | Expand for 12-24V carrier
EMC Basics | Medium | Re-qualify product connectors
Linux lab SoC | TG-524 ordered/mock | MT798X on OpenWrt
Carrier Board | None — New | Custom CCI carrier
IEC61850 | None — New | MMS + GOOSE
Secure Boot | None — New | HAB + signed images
Ethernet Segmentation | None — New | Eth_A / Eth_B / Plant
IEC62443 | None — New | SL / zones