## Risk_Register
ID | Category | Description | Impact | Likelihood | Mitigation | Owner | Status | RAG_ref
R-ISO-001 | Network | Eth_A/Eth_B not physically/logically isolated | Grid rejection / audit fail | M | Dual PHY or managed switch; strict VLAN; no shared L2 bridge | HW | Open | cei-0-16-allegato-o
R-PF2-001 | Control | Stale meter data drives curtailment | Wrong plant state / safety | M | Timestamp+validity; timeout→safe state; hysteresis | FW | Open | ccli-validation-strategy
R-SEC-001 | Cyber | Private keys in filesystem | 62351/62443 assessment fail | H | Secure element; signed images; RBAC on console | FW | Open | ccli-architecture-framework
R-BOM-001 | Process | Kit 99991105 mistaken for field CCI | Wrong procurement / false validation | M | Label all docs: kit=lab carrier=product | PM | Open | ccli-vendor-selection
R-SCH-001 | Schedule | Schematic before pin budget D3 | Respins / delay | H | Complete D3+D4 before Gerbers | HW | Open | ccli-prototype-bom
R-LIC-001 | Legal | Ship product on GPLv3 libiec61850 | License violation | H | Budget MZ commercial license from day 1 | PM | Open | ccli-project-roadmap
R-EMC-001 | EMC | RS485/CAN on kit confused with product C2 | Wrong EMC test scope | M | Re-test on carrier with opto RJ45 | HW | Open | ccli-vendor-selection
R-TIME-001 | Time | No GNSS on kit; events untimestamped in lab | False confidence in L2 | M | Mark L2 time tests as stub until C5 carrier | FW | Open | ccli-validation-strategy